## DD Full Checklist
| PROJECT TEAM KICKOFF CHECKLIST |  | KEY DATES |  | DAYS REMAINING | Days Passed
| RAP UP Portfolio, Roxbury, MA |  | LOI executed | 2025-12-22 | 0 | 204
|  |  | Seller deadline to sent DD request | 2026-01-08 | 0 | 187
|  |  | Initial Deposit ($50K) | 2026-03-20 | 0 | 116
|  |  | Rollover TS | 2026-04-19 | 0 | 86
|  |  | End of DD / 2nd Deposit ($150K) | 2026-05-19 | 0 | 56
|  |  | Buyer to send JV OA | 2026-06-18 | 0 | 26
|  |  | Seller to confirm Rollover terms | 2026-07-03 | 0 | 11
|  |  | Projected HUD Approval | 2026-08-19 | 36 | 0
|  |  | Projected Closing | 2026-09-18 | 66 | 0
|  |  | Outside Closing Date | 2026-10-16 | 94 | 0 |  |  |  | 2026-07-14
DIV Folder | Item # | Action Item | Status | Responsible Party | External Party | Outside Date | CC Comment | Partner Comment |  | Days Remaining
Equity Financing
| 1 | Create Investor log/tracker | Closed | PK |  | Ongoing |  |  | INTERNAL | -
| 2 | Draft initial investor email | Closed | PK |  | 2026-01-05 |  |  | INTERNAL | -
| 3 | Set up Smallchange account | Closed | PK |  | 2026-03-01 | $10k set up fee + 7% success fee |  | INTERNAL | -
| 4 | Finalize and confirm special GP Investor roster | Open | PK |  | 2026-07-20 | Discuss funding of 2% UPB. Send out this week. Drop individual signature blocks for individuals |  | INTERNAL | 6
| 5 | Confirm special co-GP AMF approach | Open | BA |  |  | CC internal to discuss before sending materials
| 6 | Finalize Caste investment OM | Open | BA |  | 2026-03-01 | Update OM with latest financials/deal |  | INTERNAL | 0
| Debt Financing | [8 empty] | -
| 7 | Draft list of prospective lenders to send materials | Closed | AS |  | TBC |  |  |  | -
| 8 | Create Lender OM - updated Model, S+U, OM, Rent Roll | Closed | AS |  | TBC | Update as more recent DD materials come in |  |  | -
| 9 | Create Lender tracker | Closed | AS |  | TBC | See Teams |  |  | -
| 10 | Provide feedback on loan options and impacts to business plan | Closed |  | Jacques | TBC | Going back to NM and WD for best and final |  |  | -
| 11 | W& D UW DD CHECKLIST | Open |  |  | TBC | Received. Send relevant items to UHM. Schedule call to discuss updated financials & A/R. |  |  | -
| 12 | W&D: PCA/ESA/PLAN & COST CHECKLIST | Open |  |  | TBC | Received. CC sent the materials needed. UHM must complete pipe work bbefore we close |  |  | -
| Legal - Transaction | [8 empty] | -
| 13 | Draft, review and execute PSA | Closed | PK | Nixon | 2026-03-20 | Executed 3/20 |  |  | -
| 14 | Run down cost estimates for all Goodwin legal | Closed | PK | Goodwin | 2026-02-10 | $2,900. To confirm on timing. Bank account is opened |  |  | -
| 15 | Confirm if Menkiti drafting GP JVA | Closed | PK | MG | 2026-02-15 | MG drafting |  |  | -
| 16 | Confirm if Menkiti drafting LPA (Co-GPs and OCF) | Closed | PK | MG | 2025-12-23 | MG drafting |  |  | -
| 17 | Set up JV OA: (CC, MG, OCF LP) | Open | PK | MG, Goodwin |  | Discussing with Seller |  |  | - | HUD needs draft. CC decide on date needed by
| 18 | Set GP OA: (CC, MG) | Open | PK | MG |  | MG drafting. Awaiting first draft |  |  | - | HUD needs draft. CC decide on date needed by
| 19 | Set up Caste OA: (CC Partners, Special Co-GP) | Closed | PK | Goodwin | 2026-05-01 | Document has been finalized |  | INTERNAL | -
| 20 | Set up RAP UP Partners LLC deal (CC Partners) | Closed | PK |  | 2026-05-06 | Register entity in DA. Bank needs OA, EIN, articles of incorp. DS to circulate final doc. PK to set up entity |  | INTERNAL | -
| 21 | Escrow $50K Deposit at PSA execution | Closed | PK | MG | 2026-03-27 |  |  |  | -
| 22 | Escrow $150K Deposit at DD exit | Closed | PK | MG | 2026-05-26 |  |  |  | -
| 23 | Draft / Review PMA | Closed | DS | Nixon/MG |  | Finalizing remaining language. |  |  | -
| 24 | Release Murphy Consulting on HUD 2530 Clearance | Open |  | MG / Murphy |  | In waiting mode. |  |  | -
| 25 | Confirm EOHLC's waiver | Open | PK |  | 2026-06-05 | Received 40T exemption letter on 7/13
| 26 | Lender requires No more than 3 units vacant for 90 days before closing - send message to UHM | Closed | PK
| 27 | Send Murphy Requested Information | Closed | AS |  |  | Sent 3.18.26
| 28 | Review list of deliverables for HUD 2530 Clearance | Closed |  | MG / Murphy | TBC | MG is running point. |  |  | -
| 29 | Send Walker & Dunlop PFS | Closed | AS |  | 2026-03-19 | CC/MG completed 3/20
| 30 | Send Walker & Dunlop REO | Closed | AS |  | 2026-03-19
| 31 | Review Loan Docs | Open | PK | Nixon | TBC | Call with MG Wed and Alex R on Friday morning |  |  | -
| 32 | Confirm Menkiti can fund Lender Deposit the week of close | Open | PK | MG | 2026-09-13 | Revert back in July
| 33 | Engage with Seller to complete 40T process | Closed | PK | Nixon | 2026-05-03 | Alex R (Nixon) working with confirm Ross (Seller) to submit. Ross has submitted |  |  | -
| 34 | HAP Application | Open | DS | Nixon | 2026-08-07 | Still need to submit: Deed (DS working to follow up with Seller on updated language), Property Management Agreement (sending to Kelly today)
| 35 | Draft Rollover Term Sheet (eg JV OA) | Closed | AS | Nixon | 2026-07-03 |  |  |  | -
| 36 | Finalize pre-dev/deposit funding structure agreement | Closed |  | MG | 2026-03-27 | PSA executed. Caste to send ASAP |  |  | -
| 37 | Review existing HAP Contract and prepare Assumption | Closed | PK | Nixon, Jacques | 2026-04-06 | Ask Nixon for copy of HAP contract and exhibits |  |  | -
| 38 | Send Darryl finalized DD External list (within 3 days of LOI execution) | Closed | AS | [5 empty] | -
| Physical DD + CapEx Plan | [8 empty] | -
| 39 | Engage Property Inspection Firm for full property review | Closed | [6 empty] | -
| 40 | Physical Reports / Property Condition Reports | Closed | DS |  | 2026-05-19 | EBI released on 3/20. EBI will use drones to review roof due to inability to safely access roof during DD. |  |  | -
| 41 | Confirm HUD reqs with Nixon/Lenders (e.g. need PCR or CNA?) | Closed | DS/AS |  | 2026-01-30 | Need both PCR and HUD blessed CNA |  |  | -
| 42 | Roof Reports/Repairs/Maintenance | Closed | DS |  | 2026-03-15 | there is an existing roof report (Feb '25) |  |  | -
| 43 | Structural & Seismic Reports | Closed | DS |  | 2026-03-15 | Not typically required by lender. No existing reports available |  |  | -
| 44 | Work Orders/PM Logs (HVAC, R&M, Roof, etc.) | Closed | PK |  | 2026-03-15 | Rec'd Detailed Worklog 1/1-1/12, Summary 2025. UHM is working with IT to get detailed log for 2025. |  |  | -
| 45 | Service Agreements (list) | Closed | DS |  | 2026-03-15 | Received: pest control, snow removal and janitorial. No others |  |  | -
| 46 | Warranties (list) | Closed | DS |  | 2026-03-15 | Seller: N/A |  |  | -
| 47 | Vendor Contact List | Closed | DS |  | 2026-03-15 |  |  |  | - |  | 2026-07-01
| 48 | Utility Account Numbers List & Identification | Closed | PK |  | 2026-03-15 | Under acct # for all props and ensure they're active/any open payables |  |  | -
| 49 | Utility Allowance Schedule | Closed | DS |  | 2026-03-15 |  |  |  | -
| 50 | Special Claims History | Closed | DS |  | 2026-03-15 | Seller: N/A |  |  | -
| 51 | Repayment Agreements (if any) | Closed | DS |  | 2026-03-15 | Seller: N/A |  |  | -
| 52 | VAWA Transfer Log (if applicable) | Closed | DS |  | 2026-03-15 | Seller: N/A |  |  | -
| 53 | Reasonable Accomodation Request Log (if applicable) | Closed | DS |  | 2026-03-15 | Seller: N/A |  |  | -
| 54 | Fire Escape (5 year certs) | Closed | DS |  | 2026-03-15 | Seller: N/A |  |  | -
| 55 | HVAC Unit Inventory and Description | Closed | DS |  | 2026-03-15 | Seller: N/A |  |  | -
| 56 | Infra-red/Thermographic Scan | Closed | DS |  | 2026-03-15 | Seller: N/A |  |  | -
| 57 | Review draft CAPEX budget - Base Building and Units | Closed | DS |  | 2026-05-19 | UHM to provide responses to CC/MG follow up questions on CAPEX/OPEX |  |  | -
| 58 | Prepare questions, recommendations for CC to discuss with APR | Closed | BA | Jacques | 2026-03-15 |  |  |  | -
| 59 | Let Seller know we need to be on all RCS communications | Closed | AS |  | 2025-12-23 |  |  |  | -
| 60 | Tour portfolio and review draft Rent Comp Study w/ APR | Closed | BA |  | 2026-02-07 | Toured on 1/15 w/ Frank Molis (APR). |  |  | -
| 61 | Pay APR for the RCS | Closed | AS/BA | [5 empty] | -
| 62 | Title and Zoning review | Open | [6 empty] | -
| 63 | ALTA Survey | Open | DS |  | 2026-05-19 | Draft is FINAL until signed before closing. |  |  | 0
| 64 | Title Commitment | Closed | DS |  | 2026-06-15 | DONE |  |  | -
| 65 | Lot L Tax Issue | Open | DS |  | 2026-09-01 | Redemption of tax taking to be recorded by Seller prior to closing.
| 66 | Zoning certification | Closed | DS |  | 2026-03-15 | Lender requires zoning cert. Sam at Nixon is getting ($400/property) |  |  | -
| 67 | All City/State permits | Closed | DS |  | 2026-03-15 | Seller: N/A |  |  | -
| 68 | Easement Documents (if applicable) | Closed | DS |  | 2026-03-15 | Seller: N/A |  |  | -
| 69 | Confirm FEMA Flood Vulnerable Status | Closed | DS |  | 2026-03-15 | Feldman will confirm as part of ALTA work. Not a req from Northmarq |  |  | -
| 70 | Permits Required for Property Operation (e.g. flammable fuel storage) | Closed | DS |  | 2026-03-15 | Seller: N/A |  |  | -
| 71 | Environmental Information review | Closed | [6 empty] | -
| 72 | Phase 1 ESA | Closed | DS |  | 2026-03-15 | EBI released 3/20. Finalized |  |  | -
| 73 | Hazardous Materials report | Closed | DS |  | 2026-03-15 | Seller: N/A |  |  | -
| 74 | Geotechnical soils report | Closed | DS |  | 2026-03-15 | Seller: N/A |  |  | -
| 75 | Lead abatement/compliance report | Closed | DS |  | 2026-03-15 | Letter of Full Deleading Compliance, 11/17/1998 |  |  | -
| 76 | Mold reports/remediation | Closed | DS |  | 2026-03-15 | Seller: N/A |  |  | -
| 77 | Indoor air quality reports | Closed | DS |  | 2026-03-15 | Seller: N/A |  |  | -
| 78 | Water intrusion/moisture issues | Closed | DS |  | 2026-03-15 | Seller: N/A |  |  | -
| 79 | Request Drawings + confirm building Specs | Closed | DS | [5 empty] | -
| 80 | Site Plans/Building Plans / Construction Plans / As-Builts | Closed | DS |  | 2026-03-15 | Seller: N/A |  |  | -
| 81 | Building Permits | Closed | DS |  | 2026-03-15 | Seller: N/A |  |  | -
| 82 | Certificates of Occupancy | Closed | DS |  | 2026-03-15 | Received all but one. 63 Lambert does not exist. See Zoning Cert from Title Company's attorney. CC to decide whether to clean up post-closing |  |  | -
| 83 | Building areas - Building GSF, Unit RSF's | Closed | DS |  | 2026-03-15 | Seller: N/A |  |  | -
| 84 | REAC reports and scores from prior 3 years | Closed | CC |  | 2026-03-15 | Rec'd 2025, Seller: Only one score from past 5 years |  |  | -
| 85 | Capital Needs Assessment | Closed | DS | UHM |  | Finalized and submitted to HUD |  |  | -
| 86 | Keith Construction budget | Closed | DS |  | 2026-03-15 |  |  |  | -
| 87 | Finalize pre-dev budget costs | Closed | DS |  |  | Latest sent on 4/1 |  |  | -
| 88 | Prepare microsoft GANTT chart from DD to closing | Closed | DS | [5 empty] | -
| Property Management DD | [8 empty] | -
| 89 | Review Residential Leases & House Rules | Closed | Closed |  | 2026-03-15 | Rec'd House Rules, Form Lease, need all leases, LEASES ON SITE NEED TO REVIEW |  |  | -
| 90 | Review License Agreements (if applicable) | Closed | DS |  | 2026-03-15 | Seller: N/A |  |  | -
| 91 | Review Indemnities (if applicable) | Closed | DS |  | 2026-03-15 | Seller: N/A |  |  | -
| 92 | Schedule calls with UHM to review (DD materials, budget). Walk property with onsite team | Closed | BA |  | 2026-04-17 | Intro call on 1/21. Held pre-DD prelim calls to discuss MOR/AR & delinquencies, 2026 budget, 2025 actuals. Walk through set for 4/17 |  |  | -
| 93 | 2026 Operating Budget | Closed | DS/BA |  | 2026-04-14 |  |  |  | -
| 94 | Management & Occupancy Review past 3 years | Closed | CC | Jacques | 2026-03-15 | Jacques + CC reviewed. Discussed with UHM on 1/29 |  |  | -
| 95 | Personal Property Inventory | Closed | DS |  | 2026-03-15 | Seller: N/A |  |  | -
| 96 | Photographs | Closed | DS |  | 2026-03-15 |  |  |  | -
| 97 | Review UHM's in-place management process | Closed |  |  | 2026-03-15 |  |  |  | -
| 98 | Sample 50059 files including one current resident with recertification and one former tenant | Closed | DS |  | 2026-03-15 |  |  |  | -
| 99 | Original HAP Contract | Closed | CC | Nixon | 2026-03-15 | CC to review. Need to read in person as PDF is ineligible. AS to abstract |  |  | -
| 100 | HAP Billing Files (HUD 52670A) - YTD and prior year | Closed | DS |  | 2026-03-15 |  |  |  | -
| 101 | Tenant Selection Plan | Closed | DS |  | 2026-03-15 |  |  |  | -
| 102 | Affirmative Fair Housing Marketing Plan | Closed | DS | Jacques | 2026-03-15 | Document says existing plan expired 1/31/2021. Latest plan per UHM |  |  | -
| 103 | Enterprise Income Verification (EIV) Master File | Closed | DS |  | 2026-03-15 | Requires HUD approval, need update from UHM |  |  | -
| 104 | Extended Use Agreement (if applicable) | Closed | DS |  | 2026-03-15 | Seller: N/A |  |  | -
| 105 | Current Waitlist | Closed | DS |  | 2026-03-15 |  |  |  | -
| 106 | Recent Management and Occupancy Review (MOR) reports from last 3 years | Closed | DS | Jacques | 2026-03-15 | Date of report is 8/18/25 but document says expiration 4/30/2018? Please confirm there were no other MORs completed under current ownership. And confirm the difference between this document and (29) MOR. This is a typo - these reports don't expire; The report in this folder should be with the other MOR reports |  |  | -
| 107 | Any non-compliance agency or audit findings from last 3 years | Closed | DS |  | 2026-03-15 | Seller: N/A |  |  | -
| 108 | Get sample audit of UHM files with UpLvL | Closed | DS | Jacques |  | UpLVL declined |  |  | -
| 109 | Most recent RCS & any relevant information provided; General update to progress of new RCS | Closed | BA |  | 2026-03-15 | Have RCS from 2020. Confirm if any other RCS available. Received draft RCS supporting underwritten rents. |  |  | -
| 110 | Review UHM tenant selection plan and Affordable Fair market housing plan (AFMHP) | Closed | DS/BA | Jacques | 2026-03-15 |  |  |  | -
| 111 | Set up weekly meeting with UHM team to discuss | Closed | PK | [5 empty] | -
| 112 | JVA to prepare summary of findings on review of UHM | Closed |  | Jacques |  | Materials sent; MG reviewing |  |  | -
| Property Financial DD | [8 empty] | -
| 113 | Review of Property Tax, Legal, Insurance docs | Open | [6 empty] | -
| 114 | Insurance Policies/Summary Docs/Exclusions | Open | AS |  | 2026-05-19 | GNY GL, Excess Policy from GNY & AXIS. Expires 10/2026, Travelers Property Insurance |  |  | 0
| 115 | Submit/get property insurance quotes for RAP | Open | AS |  | 2026-05-19 | McGriff - Property Insurance. Getting pricing this week. W&D is reviewing Freddie reqs on what is needed that is differenet from inplace policy. In-place works for Freddie. |  |  | 0
| 116 | Cross Insurance - confirm in-place meets Freddie | Closed | AS |  | 2026-07-03 | Confirmed 7/3 |  |  | -
| 117 | Cross Insurance - provide standalone quote | Open | AS |  | 2026-05-19 |  |  |  | 0
| 118 | Summary of Litigation Pending or in Progress | Open | AS |  | 2026-05-19 | 5 tenants pending litigation |  |  | 0
| 119 | Summary of Outstanding Insurance Claims | Closed | AS |  | 2026-05-19 |  |  |  | -
| 120 | Tax Appeals / Reduction History | Closed | AS |  | 2026-05-19 |  |  |  | -
| 121 | Tax Bills YTD + 3 prior years (including unsecured personal property) | Closed | AS |  | 2026-05-19 |  |  |  | -
| 122 | Total Insured Value (TIV) / Claims and Loss History - prior 3 years | Closed | AS |  | 2026-05-19 |  |  |  | -
| 123 | Property Management Agreement | Closed | AS |  | 2026-05-19 |  |  |  | -
| 124 | Review Historical Financials (Accounting/Finance) | Closed |  |  | 2026-05-19 |  |  |  | -
| 125 | Aged Receivable / Delinquency Report YTD (update if available) + 3 prior years | Open | BA | Jacques | 2026-05-19 | Continue to track |  |  | 0
| 126 | Appraisals | Closed | BA | Jacques | 2026-05-19 |  |  |  | -
| 127 | Detailed Operating Budget YTD + 3 prior years | Closed | BA | Jacques | 2026-05-19 | Met on 1/30 to review with UHM. Review cleaned budget Jeff Caputi sent on 3/11 |  |  | -
| 128 | Capital Expenditures - Historical (3 prior years) & 2026 Budget | Closed | BA/DS | Jacques | 2026-05-19 |  |  |  | -
| 129 | Deferred Maintenance | Closed | BA | Jacques | 2026-05-19 |  |  |  | -
| 130 | Rent Statements YTD + 3 prior years | Closed | BA | Jacques | 2026-05-19 |  |  |  | -
| 131 | Security Deposits Schedule | Closed | BA | Jacques | 2026-05-19 |  |  |  | -
| 132 | Tenant Billing Register YTD + 3 prior years | Closed | BA | Jacques | 2026-05-19 |  |  |  | -
| 133 | Utility Bills - 12 months | Closed | BA | Jacques | 2026-05-19 |  |  |  | -
| 134 | Vendor Bills - 3 prior years | Closed | BA | Jacques | 2026-05-19 |  |  |  | -
| 135 | Reach out to Ryan Tax for property tax analysis; confirm pricing | Closed | AS |  | 2026-05-19 | $2,000 for full portfolio. Ryan can kick invoice to sale. Sent latest estimates on 5/18 |  |  | -
| 136 | Provide cost cutting recommends to CC | Closed |  | Jacques | 2026-05-19 |  |  |  | -
| 137 | Schedule call to review financials with Seller/UHM post initial DD review | Closed | BA |  | 2026-05-19 |  |  |  | -
| 138 | HUD Withdrawl Request for CAPEX Reserve | Open | DS | Nixon | 2026-06-15 | Nixon is preparing request forms. Will be confirmed closer to closing
| 139 | HUD Suspension Request for CAPEX Reserve | Open | DS | Nixon | 2026-08-01 | To be submitted after Withdrawal request is approved. Requires confirmation of Lender reserve amount.
| 140 | Finalize base case underwriting model | Open | BA |  | 2026-05-19 |  |  |  | 0
| ASSET MANAGEMENT | [8 empty] | -
| 141 | Create 'Property Folder' in share drive | Open | AS |  | Ongoing |  |  |  | -
| 142 | Extract Acquisition DD files and add to Prop. Folder | Open | AS |  | Ongoing |  |  |  | -
| 143 | Set up weekly Project Team meetings | Open | AS |  | Ongoing |  |  |  | -
| 144 | Closing Model into AM Template (inc. Bridge) | Open | AS |  | Ongoing |  |  |  | -
still need
Note on G5: Bode: THIS PURCHASE AND SALE AGREEMENT (this “Agreement”) is made and entered into as of the 20th day of March, 2026 (the “Effective Date”),
Note on G7: Bode: Purchaser shall have until 5:00 PM on that date which is sixty (60) days after the Effective Date (such period being referred to herein as the “Investigation Period”), to

## Internal - DD Request List
| DUE DILIGENCE REQUEST LIST |  | UPDATED AS OF:
| RAP UP Portfolio |  | 2026-01-13
2026-07-14
DIV Folder | Item # | Document | Status | Department | Responsible Party | DIV Comment | Partner Comment | Notes
LEASING & MARKETING
| 1 | Review Residential Leases & House Rules | Open | Leasing / Marketing |  |  |  | Rec'd House Rules, Form Lease, need all leases, LEASES ON SITE NEED TO REVIEW
| 2 | Review License Agreements (if applicable) | Closed | Leasing / Marketing |  |  |  | Seller: N/A
| 3 | Review Indemnities (if applicable) | Closed | Leasing / Marketing |  |  |  | Seller: N/A
PHYSICAL / PROPERTY
|  | Title and Zoning review |  | Development
| 4 | ALTA Survey | Closed | Development |  |  |  | Seller: N/A
| 5 | Title Commitment | Open | Development |  |  |  | Owners & Lender Policy
| 6 | Deleted | Deleted | Deleted
| 7 | All City/State permits | Closed | Development |  |  |  | Seller: N/A
| 8 | Easement Documents (if applicable) | Closed | Development |  |  |  | Seller: N/A
| 9 | Confirm FEMA Flood Vulnerable Status | Closed | Development |  |  |  | Seller: N/A
| 10 | Permits Required for Property Operation (e.g. flammable fuel storage) | Closed | Development |  |  |  | Seller: N/A
Environmental Information review
| 11 | Phase 1 ESA | Closed | Development |  |  |  | Seller: N/A
| 12 | Hazardous Materials report | Closed | Development |  |  |  | Seller: N/A
| 13 | Geotechnical soils report | Closed | Development |  |  |  | Seller: N/A
| 14 | Lead abatement/compliance report | Received | Development |  |  |  | Letter of Full Deleading Compliance, 11/17/1998
| 15 | Mold reports/remediation | Closed | Development |  |  |  | Seller: N/A
| 16 | Indoor air quality reports | Closed | Development |  |  |  | Seller: N/A
| 17 | Water intrusion/moisture issues | Closed | Development |  |  |  | Seller: N/A
| 18 | Deleted | Deleted | Deleted
| 19 | Deleted | Deleted | Deleted
Request Drawings + confirm building Specs
| 20 | Site Plans/Building Plans / Construction Plans / As-Builts | Closed | Development |  |  |  | Seller: N/A
| 21 | Building Permits | Closed | Development |  |  |  | Seller: N/A
| 22 | Certificates of Occupancy | Received | Development |  |  |  | Received all but one. 63 Lambert does not exist. See Zoning Cert from Title Company's attorney. CC to decide whether to clean up post-closing
| 23 | Building areas - Building GSF, Unit RSF's | Closed | Development |  |  |  | Seller: N/A
| 24 | Deleted | Deleted | Deleted
| 25 | REAC reports and scores from prior 3 years | Closed | Development |  |  |  | Rec'd 2025, Seller: Only one score from past 5 years
| 26 | Capital Needs Assessment | Closed | Development |  |  |  | 2021, Seller: CNA good for 10 years
| 27 | Keith Construction budget | Open
PROPERTY MANAGEMENT
Schedule calls with UHM to review (DD materials, budget). Walk property with onsite team
| 28 | 2026 Operating Budget | Received | Prop Mgmt
| 29 | Management & Occupancy Review past 3 years | Open |  |  |  |  | Received 2023 and 2025; No 2024 report exists
| 30 | Personal Property Inventory | Closed | Prop Mgmt |  |  |  | Seller: N/A
| 31 | Photographs | Received | Prop Mgmt
Engage Property Inspection Firm for full property review
| 32 | Physical Reports / Property Condition Reports | Closed | Prop Mgmt |  |  |  | Seller: N/A
| 33 | Roof Reports/Repairs/Maintenance | Open | Prop Mgmt |  |  |  | Feb 2025 inspection reports for all roofs. No R&M info. Seller: Requested
| 34 | Structural & Seismic Reports | Closed | Prop Mgmt |  |  |  | Seller: N/A
| 35 | Work Orders/PM Logs (HVAC, R&M, Roof, etc.) | Open | Prop Mgmt |  |  |  | Rec'd Detailed Worklog 1/1-1/12, Summary 2025. UHM is working with IT to get detailed log for 2025.
| 36 | Deleted | Deleted | Deleted
| 37 | Deleted | Deleted | Deleted
| 38 | Service Agreements (list) | Received | Prop Mgmt |  |  |  | Received: pest control, snow removal and janitorial. No others
| 39 | Warranties (list) | Closed | Prop Mgmt |  |  |  | Seller: N/A
| 40 | Vendor Contact List | Received | Prop Mgmt
| 41 | Utility Account Numbers List & Identification | Received | Prop Mgmt
| 42 | Utility Allowance Schedule | Received | Prop Mgmt
| 43 | Special Claims History | Closed | Prop Mgmt |  |  |  | Seller: N/A
| 44 | Repayment Agreements (if any) | Closed | Prop Mgmt |  |  |  | Seller: N/A
| 45 | VAWA Transfer Log (if applicable) | Closed | Prop Mgmt |  |  |  | Seller: N/A
| 46 | Reasonable Accomodation Request Log (if applicable) | Closed | Prop Mgmt |  |  |  | Seller: N/A
| 47 | Fire Escape (5 year certs) | Closed | Prop Mgmt |  |  |  | Seller: N/A
| 48 | HVAC Unit Inventory and Description | Closed | Prop Mgmt |  |  |  | Seller: N/A
| 49 | Infra-red/Thermographic Scan | Closed | Prop Mgmt |  |  |  | Seller: N/A
| 50 | Deleted | Deleted | Deleted
AFFORDABLE
Review UHM's in-place management process
| 51 | Sample 50059 files including one current resident with recertification and one former tenant | Received | Prop Mgmt
| 52 | Original HAP Contract | Received | Prop Mgmt
| 53 | HAP Billing Files (HUD 52670A) - YTD and prior year | Received
| 54 | Tenant Selection Plan | Received | Prop Mgmt
| 55 | Affirmative Fair Housing Marketing Plan | Received | Prop Mgmt |  |  |  | Document says existing plan expired 1/31/2021. Latest plan per UHM
| 56 | Enterprise Income Verification (EIV) Master File | Open |  |  |  |  | Requires HUD approval, need update from UHM
| 57 | Extended Use Agreement (if applicable) | Closed | Prop Mgmt |  |  |  | Seller: N/A
| 58 | Current Waitlist | Received | Prop Mgmt |  |  |  | Dated 1/6/26
| 59 | Recent Management and Occupancy Review (MOR) reports from last 3 years | Received | Prop Mgmt |  |  |  | Date of report is 8/18/25 but document says expiration 4/30/2018? Please confirm there were no other MORs completed under current ownership. And confirm the difference between this document and (29) MOR. This is a typo - these reports don't expire; The report in this folder should be with the other MOR reports
| 60 | Any non-compliance agency or audit findings from last 3 years | Closed | Prop Mgmt |  |  |  | Seller: N/A
| 61 | Most recent RCS & any relevant information provided; General update to progress of new RCS | Received |  |  |  |  | In progress, Contract with CC.
LEGAL, INSURANCE AND TAX DOCUMENTS
Review of Property Tax, Legal, Insurance docs
| 62 | Insurance Policies/Summary Docs/Exclusions | Received | Legal/Ins/Tax |  |  |  | GNY GL, Excess Policy from GNY & AXIS. Expires 10/2026, Travelers Property Insurance
| 63 | Summary of Litigation Pending or in Progress | Received | Legal/Ins/Tax |  |  |  | 5 tenants pending litigation
| 64 | Summary of Outstanding Insurance Claims | Received | Legal/Ins/Tax |  |  |  | None
| 65 | Tax Appeals / Reduction History | Open | Legal/Ins/Tax
| 66 | Tax Bills YTD + 3 prior years (including unsecured personal property) | Open | Legal/Ins/Tax |  |  |  | 2025: Only Q2 and Q3 provided? 2024: Only Q1 and Q3 provided? 2023: Only Q3 provided? 2022: Only Q4 provided?
| 67 | Total Insured Value (TIV) / Claims and Loss History - prior 3 years | Received | Legal/Ins/Tax
| 68 | Property Management Agreement | Received | Legal/Ins/Tax
ACCOUNTING / FINANCE
Review Historical Financials (Accounting/Finance)
| 69 | Aged Receivable / Delinquency Report YTD (update if available) + 3 prior years | Received | Accounting |  |  |  | 2023,2024, 2025, YTD thru 1/5
| 70 | Appraisals | Received | Accounting
| 71 | Detailed Operating Budget YTD + 3 prior years | Received | Accounting
| 72 | Capital Expenditures - Historical (3 prior years) & 2026 Budget | Open | Accounting
| 73 | Deferred Maintenance | Open | Accounting
| 74 | Rent Statements YTD + 3 prior years | Received | Accounting |  |  |  | 2023, 2024, 2025
| 75 | Security Deposits Schedule | Open | Accounting
| 76 | Tenant Billing Register YTD + 3 prior years | Received | Accounting
| 77 | Utility Bills - 12 months | Received | Accounting
| 78 | Vendor Bills - 3 prior years | Received | Accounting
still need

## HAP Assignment Checklist
HAP Assignment Checklist (with HUD Exhibit 2 items)
General Information
Name: |  |  | How does 2530 HUD Clearance layer into this? |  | Seller:
Address: |  |  | Any docs we need to get Darryl now? |  | FHA:
Contract: |  |  |  |  | PBCA:
New Owner: |  |  |  |  | HUD AE:
Section 1 |  | Proposed Owner Information | Responsible Party | CC/MG Notes | Status | Comments
| a. | Name and signature block for Proposed Owner entity | John Daniels |  |  | Borrower Name:
| b. | Organizational Chart for Proposed Owner entity (with percentage interests and roles for all entities and individuals) | Caste - Nixon
| c. | Resume for Proposed Owner or sponsor (include any affordable experience) | John Daniels | Will this be both CC and MG?
| d. | Articles of Organization/Certificate of Formation/Certificate of Limited Partnership | John Daniels |  |  | State of Formation:
| e. | Operating Agreement/Limited Partnership Agreement | John Daniels |  |  | Date of Operating Agreement:
| f. | 2530 Previous Participation submission confirmation in APPS | John Daniels |  |  | APPS Submission Number: Confirm entities are registered in Business Partner Registration if paper 2530 is submitted in lieu of APPS submission.
| g. | Real Estate Owned (REO) Schedule | John Daniels | Will this be both CC and MG? Trace control
| h. | Purchaser's Financial Statement (HUD Form 92417) | John Daniels | Will this be both CC and MG? Trace control
| i. | Unique Entity ID Registration Confirmation | John Daniels | Will this be both CC and MG? Trace control |  | Unique Entity ID:
| j. | EIN Number for Proposed Owner entity | John Daniels | Will this be both CC and MG? Trace control |  | EIN Number:
| k. | Confirmation of Fiscal Year End Date | John Daniels | Will this be both CC and MG? Trace control
| l. | Certificate of Good Standing | John Daniels | Will this be both CC and MG? Trace control
| m. | Authorizing Resolution | John Daniels | Will this be both CC and MG? Trace control
| n. | Credit Report for sponsor | John Daniels | Will this be both CC and MG? Trace control
Section 2 |  | Management Company Information
| a. | Resume of Management Company | Caste | From UHM |  | Name of Management Agent:
| b. | Management Agent Certification (HUD Form 9839-B) | N/A | N/A with UHM staying in place?
If new management is being retained at closing:
| c. | Management Entity Profile (HUD Form 9832) | Caste | From UHM
| d. | 2530 Previous Participation submission confirmation on APPS | Caste | From UHM |  | APPS Submission Number: Confirm entities are registered in Business Partner Registration if paper 2530 is submitted in lieu of APPS submission.
| e. | Proposed Tenant Selection Plan | Caste | From UHM
| f. | Proposed Tenant Lease | Caste | From UHM |  | Need confirmation that the agent will use the HUD form model lease (form HUD-90105a)
| g. | Management Agreement with HUD required provisions | Caste | Can we use current or needs to be assigned?
Section 3 |  | Project Finances and Affordability
| a. | Description of financing (LIHTC? Conventional? FHA? Tax-exempt bonds?) | Caste | Will likely be TBD prior to submission. Ok to follow
| b. | Pro Forma Net Operating Income | Caste
| c. | Pro Forma Sources and Uses | Caste
| d. | Estimated closing date | Caste |  |  | Closing Date:
| e. | Purchase and Sale Agreement and any amendments or assignments | Caste |  |  | Executed Date:
| f. | Name and address of Lender | Caste |  |  | Lender Name:
| g. | Name and address of Title Company/Escrow Agent | Caste |  |  | Title Name:
| h. | Proposed Deed | Caste
| i. | Balance Sheet | Caste
| j. | Lender's Reserve Requirement (both initial deposit and PUPY amounts) | Caste
| k. | Draft Financing Documents | Caste
| l. | Lender Term Sheet or Financing Commitment | Caste
| m. | LIHTC Documents (if applcable - includes LIHTC lease rider, draft tax credit use agreement, etc.) | N/A
| n. | Consent to Assignment of HAP Contract | Caste - Nixon | Is this a pre-consent agreement before executing the assignment? Or consent from lender? |  | Need confirmation of Fannie, Freddie, or Conventional Financing along with lender name and address
Section 4 |  | Property Information
| a. | Unit count and configuration | Caste
| b. | HAP Original Contract | Caste |  |  | Limitation on Distributions – Yes/No Reserve for Replacement Requirement – Yes/No
| c. | Copies of prior HAP Assignments, if applicable | Caste
| d. | HAP Renewal Contract | Caste |  |  | Effective Date:
| e. | Current Rent Schedule | Caste |  |  | Effective Date:
| f. | Utility Allowance (if tenant-paid, date of most recent UA baseline) | Caste
| g. | Scope of Work | Caste
| h. | Relocation Plan, if applicable | N/A
| i. | Property Condition Report (PCR) or Project Capital Needs Assessment (PCNA) via the eTool | Caste | From what time period? CNA from 2021, CC will likely do PCR and/or CNA depending on requirements. Needs to be recent and need CNA with Vendor familiar with HUD |  | Need copy of final report and automated email from HUD confirming the reviewer of the submitted report via HUD’s online eTool
| j. | Latest REAC Inspection Report | Caste |  |  | REAC Score and Date:
| k. | Latest MOR Inspection Report | Caste |  |  | MOR Result and Date:
| l . | Financial Audits for two previous years | Caste | Have 2023 and 2024, not sure timing of 2025. 2023 and 2024 okay
| m. | Interim Financial Statements for the Project (i.e. trailing 12-month) | Caste
| n. | Title Commitment | Caste
| o. | HUD Use Agreements, if applicable | Caste | Confirm if applicable
| p. | Service Coordinator Grant, if applicable | Caste | Confirm if applicable

## Lender Checklist
Northmarq - Lender Checklist
PRIORITY CREDIT ITEMS FOR RATE LOCK | [5 empty] | Walker
TBD BORROWING ENTITY | [6 empty] | SENT
1 | Organizational Chart | Closed | AS |  | Draft from 1.7.26 | January T-12 Operating Statement (Dec. will suffice)
2 | Organizational Documents (exec. When available) | Open | AS |  | RAP UP Partners, LLC OA | Current Rent Roll
3 | Credit Authorization / Loan History Statement | Open | AS |  |  | Schedule of recent Cap Ex repairs (within last two years)
4 | Current Balance Sheet | Open | AS |  |  | Name of proposed management company, summary of their experience, highlighing scattered site and Section 8
Resume/bios for key principals
TBD KEY PRINCIPAL / GUARANTOR | [5 empty] | Schedule of REO - unit, occupancy, maturity dates, current lender, noi, market value, DSCR, LTV
5 | Driver's License or Passport | Open | AS |  |  | Financial statements for Caste
6 | Biography detailing REO & Mgmt Experience | Open | AS
7 | Credit Authorization / Loan History Statement | Open | AS
8 | Personal Financial Statements | Open | AS
9 | RE Schedule and Explanations for all contignecy liabilities | Open | AS
10 | Verification of Deposits (bank or brokers statements dated within 3 months will suffice) | Open | AS
TBD PRINCIAL INDIVIDUALS
11 | Driver's License or Passport | Open | AS
12 | Biography detailing REO & Mgmt Experience | Open | AS
13 | Credit Authorization / Loan History Statement | Open | AS
14 | Personal Financial Statements | Open | AS |  | From Who?
TBD PRINCIPAL ENTITIES
15 | Organization Documents (exec. When available) | Open | AS
16 | Credit Authorization / Loan History Statement | Open | AS
17 | Current Balance Sheet | Open | AS
PROPERTY-LEVEL ITEMS FOR RATE LOCK
OPERATING STATEMENTS
18 | Historical P&Ls (3 yrs as avail.) | Closed | AS |  | Uploaded, 2025 thru 11/25
19 | Current Monthly T-12 | Closed | AS |  | Included in 18, T-12 from 11/25
20 | Borrower's Current Budget | Open | AS
21 | Current Rent Roll(s) (detailed) | Closed | AS |  | As of 12.31.25
22 | Collections - 3 months of operating account bank statements for account name to Borrower/Owner | Open | AS
23 | Collections - Delinquency/Aged Receiveables & Prepaid Report | Closed | AS |  | As of 12.31.25
24 | CapEx - Sponsor's recently completed improvements & Lender's receipt of a detailed Cap Ex budget | Open | AS
25 | Borrower expense comparables for similar properties owned in similar markets (current or prior year P&L data will suffice) | Open | AS
26 | Property payroll summary | Open | AS
27 | Cert. of Occ. - if readily available | Closed | AS |  | 63 Lambert not included
INSURANCE, LEGAL, & THIRD-PARTY ITEMS REQUIRED FOR RATE LOCK
INSURANCE, LEGAL, & THIRD-PARTY ITEMS
28 | Lender's acceptable insurance review of property and liability insurance policies (inc. Accord 25, 27) and annual premium quote | Open | AS |  | Getting quote from McGriff, current: Traveler's
29 | Lender inspection with acceptable findings (acceptable review of corporate units, leases, tenant ledgers, etc.) | Open | AS | Northmarq
30 | Executed Current Management Contract (or proposed) – explicitly stating compensation. | Open | AS
31 | ALTA Survey / Title Policy Commitment | Open | AS |  | ALTA expected mid-March, 6 weeks from release
32 | Acceptable Review of: Appraisal | Open | AS | Northmarq
33 | Acceptable Review of: PCA and Enviro Report indications including approach to radon testing and mitigation, required O&M reports, and WDI report, if needed | Open | AS |  | EBI, mid-March, 6 weeks from release
34 | Acceptable Review of: Lender's review of zoning report | Open | AS | Northmarq
35 | Good Faith Deposit Confirmation | Open | AS
36 | Title Company / Escrow Agent receipts and disbursements ledger for the transaction showing: Source of all funds deposited (with federal fund wires and full entity names) in the closing escrow) The flow of all funds disbursed from the closing escrow to the Mortage Loan | Open | AS
37 | Fannie Mae approval of Loan Doc Mods (if any) | Open | AS
38 | UCC/Tax Lien/Judgement Searchs - for Borrowing entite, key principals, guarantor (will be ordered by Lender Counsel) | Open | AS
39 | Additional RL items noted in Legal check list | Open | AS
40 | Copy of Current Note and Payoff Letter | Open | AS
41 | Underwriting Certificate (will be prepared for signatures at a later date) | Open | AS
OTHER ITEMS REQUIRED FOR CLOSING
OTHER
42 | W-9 Tax Identification Certification - for Borrowing Entity | Open | AS
43 | Preliminary Estimate of Sources and Uses | Open | AS
44 | ACH Form & Voided Check - for Borrowing Entity | Open | AS

## Deal Team
Role | Organization | Name
Acquiror | Caste Capital | Bode Adunbarin
Acquiror | Caste Capital | David Stewart
Acquiror | Caste Capital | Patrick Kimble
Acquiror | Caste Capital | Alex Schultz
Acquiror | Menkiti Group | Bo Menkiti
Acquiror | Menkiti Group | John Daniels
Acquiror/Seller | Catalyst Ventures | Darryl Settles
Broker | Colliers | Jeanne Pinnado
Legal Counsel | Nixon Peabody | Alex Rosso
HAP Contract Administrator | MassHousing | TBC
3P - Physical Needs Assessor | TBC | TBC
3P - Environment Consultant | TBC | TBC
3P - Surveyor/Contractor | TBC | TBC
3P - Rent Comp Study | APR | Joe Antonelli
Debt Financing (Option) | Rockport | Linda Pellegrino, James Beghai
Debt Financing (Option) | Northmarq | Jeff Munoz
Debt Financing (Option) | Brookline Bank | Robert Page
Debt Financing (Option) | W&D | John Gregory, John Gilmore
Debt Financing (Option) | Citizens | Jon Reidinger
Debt Financing (Option) | Eastern Bank | Angela Meehan
Debt Financing (Option; received LOIs) | Hingam and Webster 5 | Paul J. Barry
Debt Financing (Option) | LISC | Gustavo Quiroga

## Cost Schedule
DD SCHEDULE / COST TRACKER
| Phase | Task | Party | Start | Duration | End | Budget | Proposal Cost | Spent | Remaining | 2025-12-22 | 2026-01-31 | 2026-02-28 | 2026-03-31 | 2026-04-30 | 2026-05-31 | 2026-06-30 | 2026-07-31 | 2026-08-31 | 2026-09-30 | CHECK
| Acquisition - Legal | Execute LOI | Acquiror/Seller | 2025-12-22 | 0 | 2025-12-22 | 0.0001 | 0.0001 | 0.0001 | 0 | 0.0001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Acquisition - Legal | Draft and execute PSA | Acquiror | 2025-12-22 | 40 | 2026-01-31 | 7500 | 7500 | 0 | 7500 | 0 | 0 | 0 | 0 | 0 | 7500 | 0 | 0 | 0 | 0 | 0
| Acquisition - Legal | Draft and execute LPA, JVAs | Acquiror/Seller/Nixon | 2025-12-22 | 40 | 2026-01-31 | 10000 | 10000 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0
| Acquisition - Legal | Draft and execute Caste GP formation doc | CC, Nixon | 2025-12-22 | 40 | 2026-01-31 | 2500 | 2500 | 0 | 2500 | 0 | 0 | 0 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 0
| DD / HUD Approvals | Mgmt agent and ownership approvals, HAP Contract Review & Assumption | Acquiror, Seller, Nixon Peabody, MassHousing | 2026-01-31 | 120 | 2026-05-31 | 35000 | 35000 | 0 | 35000 | 0 | 0 | 0 | 0 | 0 | 35000 | 0 | 0 | 0 | 0 | 0
| Acquisition - Legal | Draft and execute PMAs | Acquiror/Seller/Nixon | 2025-12-22 | 40 | 2026-01-31 | 12500 | 12500 | 0 | 12500 | 0 | 0 | 0 | 0 | 0 | 12500 | 0 | 0 | 0 | 0 | 0
| Due Diligence | Zoning Certificate / Letter | Acquiror, 3Ps | 2026-02-01 | 60 | 2026-04-02 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Due Diligence | Title Review | Acquiror, 3Ps | 2026-02-01 | 60 | 2026-04-02 | 5000 | 5000 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0
| Due Diligence | Order ALTA Survey | Acquiror, 3Ps | 2026-02-01 | 60 | 2026-04-02 | 45000 | 40000 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0
| Due Diligence | Order PCA/CNA | Acquiror, 3Ps | 2026-02-01 | 60 | 2026-04-02 | 60000 | 8050 | 0 | 8050 | 0 | 0 | 0 | 6037.5 | 2012.5 | 0 | 0 | 0 | 0 | 0 | 0
| Due Diligence | Phase I ESA | Acquiror, 3Ps | 2026-02-01 | 60 | 2026-04-02 | 60000 | 13200 | 0 | 13200 | 0 | 0 | 0 | 9900 | 3300 | 0 | 0 | 0 | 0 | 0 | 0
| Due Diligence | Misc | Acquiror, 3Ps | 2026-02-01 | 60 | 2026-04-02 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Due Diligence | Rent Comp Study | Acquiror, APR | 2026-01-31 | 45 | 2026-03-17 | 0 | 7000 | 0 | 7000 | 0 | 0 | 7000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Due Diligence | 2530 Clearance Work | Acquiror, APR | 2026-01-31 | 45 | 2026-03-17 | 0 | 7500 | 0 | 7500 | 0 | 0 | 0 | 3750 | 3750 | 0 | 0 | 0 | 0 | 0 | 0
| Due Diligence | Ryan Tax Report | Acquiror, 3Ps | 2026-02-01 | 60 | 2026-04-02 | 0 | 2000 | 0 | 2000 | 0 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Financing | Lender legal fees | Acquiror, Lender, Nixon | 2026-02-01 | 60 | 2026-04-02 | 27000 | 15000 | 0 | 15000 | 0 | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Financing | Lender Reports & fees | Acquiror, Lender, Nixon | 2026-02-01 | 60 | 2026-04-02 | 20000 | 28000 | 0 | 28000 | 0 | 0 | 0 | 28000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Due Diligence | Affordable consultant | Acquiror, Jacques | 2026-01-31 | 120 | 2026-05-31 | 50500 | 50500 | 0 | 50500 | 0 | 0 | 0 | 0 | 0 | 50500 | 0 | 0 | 0 | 0 | 0
| Contingency |  |  | 2025-12-22 | 40 | 2026-01-31 | 0 | 19325 | 0 | 19325 | 0 | 0 | 0 | 0 | 0 | 19325 | 0 | 0 | 0 | 0 | 0
| Deposit #1 | Escrow deposit ($50K at PSA signing) | Acquiror | 2026-01-31 | 5 | 2026-02-05 | 50000 | 50000 | 0 | 50000 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Deposit #2 | Escrow deposit ($150K at DD) | Acquiror | 2026-04-01 | 5 | 2026-04-06 | 150000 | 150000 | 0 | 150000 | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0
| Total (Incl. Deposits) | [5 empty] | 545000.0001 | 463075.0001 | 0.0001 |  | 0.0001 | 0 | 57000 | 64687.5 | 159062.5 | 182325 | 0 | 0 | 0 | 0 | 0
| Total (Excl. Deposits) | [5 empty] | 345000.0001 | 263075.0001 | 0.0001 |  | 0.0001 | 0 | 7000 | 64687.5 | 9062.5 | 182325 | 0 | 0 | 0 | 0 | 0
| Note: | [9 empty] | 2026-01-31: 0; 2026-02-28: 28500; 2026-03-31: 32343.75; 2026-04-30: 79531.25; 2026-05-31: 91162.5
| Dates are approximations. | [9 empty] | 2026-01-31: 0; 2026-02-28: 3500; 2026-03-31: 32343.75; 2026-04-30: 4531.25; 2026-05-31: 91162.5
[12 empty] | 0 | 875 | 8085.9375 | 1132.8125 | 22790.625

## External - DD List (hidden)
| DUE DILIGENCE REQUEST LIST |  | 2025-12-01
RAP UP Portfolio
2026-07-14
DIV Folder | Item # | Document | Status | Department | Responsible Party | DIV Comment | Partner Comment
LEASING & MARKETING
| 1 | Residential Leases & House Rules | Open | Leasing / Marketing
| 2 | License Agreements (if applicable) | Open | Leasing / Marketing
| 3 | Indemnities (if applicable) | Open | Leasing / Marketing
PHYSICAL / PROPERTY
|  | Title and Zoning | Open | Development
| 4 | ALTA Survey | Open | Development
| 5 | Existing Title Insurance Policy | Open | Development
| 6 | Deleted | Deleted | Deleted
| 7 | All City/State permits | Open | Development
| 8 | Easement Documents (if applicable) | Open | Development
| 9 | Confirm FEMA Flood Vulnerable Status | Open | Development
| 10 | Permits Required for Property Operation (e.g. flammable fuel storage) | Open | Development
Environmental Information
| 11 | Phase 1 and 2 ESA | Open | Development
| 12 | Hazardous Materials report | Open | Development
| 13 | Geotechnical soils report | Open | Development
| 14 | Lead abatement/compliance report | Open | Development
| 15 | Mold reports/remediation | Open | Development
| 16 | Indoor air quality reports | Open | Development
| 17 | Water intrusion/moisture issues | Open | Development
| 18 | Deleted | Deleted | Deleted
| 19 | Deleted | Deleted | Deleted
Drawings
| 20 | Site Plans/Building Plans / Construction Plans / As-Builts | Open | Development
| 21 | Building Permits | Open | Development
| 22 | Certificates of Occupancy | Open | Development
| 23 | Building areas - Building GSF, Unit RSF's | Open | Development
| 24 | Deleted | Deleted | Deleted
| 25 | REAC reports and scores from prior 3 years | Open | Development
| 26 | Capital Needs Assessment | Open | Development
PROPERTY MANAGEMENT
| 27 | 2026 Operating Budget | Open | Prop Mgmt
| 28 | Management & Occupancy Review past 3 years
| 29 | Personal Property Inventory | Open | Prop Mgmt
| 30 | Photographs | Open | Prop Mgmt
| 31 | Physical Reports / Property Condition Reports | Open | Prop Mgmt
| 32 | Roof Reports/Repairs/Maintenance | Open | Prop Mgmt
| 33 | Structural & Seismic Reports | Open | Prop Mgmt
| 34 | Work Orders/PM Logs (HVAC, R&M, Roof, etc.) | Open | Prop Mgmt
| 35 | Deleted | Deleted | Deleted
| 36 | Deleted | Deleted | Deleted
| 37 | Service Agreements (list) | Open | Prop Mgmt
| 38 | Warranties (list) | Open | Prop Mgmt
| 39 | Vendor Contact List | Open | Prop Mgmt
| 40 | Utility Account Numbers List & Identification | Open | Prop Mgmt
| 41 | Utility Allowance Schedule | Open | Prop Mgmt
| 42 | Special Claims History | Open | Prop Mgmt
| 43 | Repayment Agreements (if any) | Open | Prop Mgmt
| 44 | VAWA Transfer Log (if applicable) | Open | Prop Mgmt
| 45 | Reasonable Accomodation Request Log (if applicable) | Open | Prop Mgmt
| 46 | Fire Escape (5 year certs) | Open | Prop Mgmt
| 47 | HVAC Unit Inventory and Description | Open | Prop Mgmt
| 48 | Infra-red/Thermographic Scan | Open | Prop Mgmt
| 49 | Deleted | Deleted | Deleted
AFFORDABLE
| 50 | Sample 50059 files including one current resident with recertification and one former tenant | Open | Prop Mgmt
| 51 | Original HAP Contract | Open | Prop Mgmt
| 52 | HAP Billing Files (HUD 52670A) - YTD and prior year | Open
| 53 | Tenant Selection Plan | Open | Prop Mgmt
| 54 | Affirmative Fair Housing Marketing Plan | Open | Prop Mgmt
| 55 | Enterprise Income Verification (EIV) Master File | Open
| 56 | Extended Use Agreement (if applicable) | Open | Prop Mgmt
| 57 | Current Waitlist | Open | Prop Mgmt
| 58 | Recent Management and Occupancy Review (MOR) reports from last 3 years | Open | Prop Mgmt
| 59 | Any non-compliance agency or audit findings from last 3 years | Open | Prop Mgmt
LEGAL, INSURANCE AND TAX DOCUMENTS
| 60 | Insurance Policies/Summary Docs/Exclusions | Open | Legal/Ins/Tax
| 61 | Summary of Litigation Pending or in Progress | Open | Legal/Ins/Tax
| 62 | Summary of Outstanding Insurance Claims | Open | Legal/Ins/Tax
| 63 | Tax Appeals / Reduction History | Open | Legal/Ins/Tax
| 64 | Tax Bills YTD + 3 prior years (including unsecured personal property) | Open | Legal/Ins/Tax
| 65 | Total Insured Value (TIV) / Claims and Loss History - prior 3 years | Open | Legal/Ins/Tax
| 66 | Property Management Agreement | Open | Legal/Ins/Tax
ACCOUNTING / FINANCE
| 67 | Aged Receivable / Delinquency Report YTD (update if available) + 3 prior years | Open | Accounting
| 68 | Appraisals | Open | Accounting
| 69 | Detailed Operating Budget YTD + 3 prior years | Open | Accounting
| 70 | Capital Expenditures - Historical (3 prior years) & 2026 Budget | Open | Accounting
| 71 | Deferred Maintenance | Open | Accounting
| 72 | Rent Statements YTD + 3 prior years | Open | Accounting
| 73 | Security Deposits Schedule | Open | Accounting
| 74 | Tenant Billing Register YTD + 3 prior years | Open | Accounting
| 75 | Utility Bills - 12 months | Open | Accounting
| 76 | Vendor Bills - 3 prior years | Open | Accounting
still need